## Sheet1- Hemant (hidden)
Phase+B2:F12 | Deliverable name | Submission Date | Status | Reviewed and final sign off by
Phase.2 | Current status of the Saudi PHA’s and business assessment | 2023-12-21 | Submitted to PHA on 18 Dec, PHA has directed to get a final review from Pesh and Dr Michelle Report submitted to experts for review | Reviewed by Pesh and Dr Michelle, and final sign off by Deepak
| Data Architecture and Functional Current State Assessment | Submitted, waiting for PHA approval | Submitted to PHA on 27 Nov, waiting for PHA approval
| Technical & IT Infrastructure assessment | Submitted, waiting for PHA approval | Submitted to PHA on 14 Dec, waiting for PHA approval
| Public health data driven organizations benchmarking and best practices | 2024-01-12 | Sadaf review and add comments on 2 Jan 2024 | Dr Sangam to emplement the comments
Phase 3 | Taxonomy and Metadata Schema Development | 2023-12-22 | Revised taxonomy and metadata schema was submitted on 14 Dec 2023 Meeting held with Eng. Abdulaziz from PHA Scientific Committee, and he suggested some changes related to mapping between the master table and organizations, remove duplicate variables, and add a lookup table in the ER diagram Team is working on the suggested changes and will be submitting the revised taxonomy by 30 January 2024 | Final sign off by Caroline Tai
| Data security | 2023-12-25 | Report will be submitted on 12 Dec 2023 Received final comments on data security process from Dr. Majed on 25 Dec 2023, Data scurity process submited on 30 Dec 2023 Team is making final changes to the report and will be submitting revised report by 05 January 2024 | Final sign off by Mohamed Elbelasy
| Data Architecture Design and Functional Requirement Development | 2023-12-26 | Revised report submitted on 15 Nov 2023 PHA suggested to include Genomics application to the overall architecture Team is working on the suggested changes and revised report will be submitted on after Oracle On-Prem respond | Final sign off by Maciej
| Technical requirements development | 2023-12-28 | Revised report submitted on 15 Nov 2023 PHA suggested to include Genomics application to the overall architecture Team is working on the suggested changes and revised report will be submitted on after Orecal respond | Final sign off by Maciej
| Software Product Recommendations | 2023-12-28 | The overall report is ready, however, we are waiting for response from Oracle on-prem team on suggested architecture. Apart from this, there are 7 RFPs which needs to be submitted which includes: - Unified Health Data Platform RFP - 6 Surveillance RFP One draft sample RFP (Survilance) was submitted to PHA on 12 Dec 2023 for feedback and it was suggested on 26 Dec 2023 that all RFPs should reviewed by experts. Team is working with PHA team to finalise the RFPs and will submit all the RFP by 31 Jan 2024 | Final sign off by Maciej

## Sheet1 (hidden)
Phase | Deliverable name | Status | Team | Reviewed | Revisions | Target Submission Date | Revised timelines | Status
Phase.2 | Current status of the Saudi PHA’s and business assessment | Submitted to PHA on 18 Dec, PHA has directed to get a final review from Pesh and Dr Michelle Report submitted to experts for review |  | Review by Pesh and Dr Michelle and final email approval |  | 2024-01-19 |  | On track
| Data Architecture and Functional Current State Assessment | Submitted to PHA on 27 Nov, waiting for PHA approval |  |  | MG has reviewed needs | 2024-01-19 |  | On track
| Technical & IT Infrastructure assessment | Submitted to PHA on 14 Dec, waiting for PHA approval |  |  |  | Submitted, waiting for PHA approval
| Public health data driven organizations benchmarking and best practices | Comments from Sadaf received on 2 Jan 2024 Report is also under review by Pesh and Dr Michelle |  | Final sign off by Pesh and Dr Michelle |  | 2024-01-19 |  | On track
Phase.3 | Draft PHA Data Strategy and Operating Model Design for internal discussion | Key stakeholder identified and prepared a draft deck for external stakeholder engagement Stakeholder-wise discussion guide is under process Meetings to be scheduled with these key stakeholders | Pesh & Michelle | Pesh and Dr Michelle will do the final sign off |  | 2024-02-19
| Final PHA Data Strategy and Operating Model Design based on PHA leader's inputs and external stakeholders workshop inputs |  | Pesh & Michelle |  |  | 2024-03-15
| Performance Metrics, Key Performance Indicators (KPIs) and Maturity model | KPIs will be defined based on finalised strategy | Pesh & Michelle |  |  | 2024-03-20
| Implementation Roadmap: the primary activities | Synthesised implementation road map will be developed based on finalised strategy | Pesh & Michelle |  |  | 2024-03-25
| Data Quality and Data Standards | Next workshop on data quality is to be conducted wherein we will have our expert to oversee steps taken by PHA on current data set and suggest in case any changes are required Refine the deliverable based on workshop and submit | Dr Sangam | Andreas will do the final sign off on the deliverable. Pesh review |  | 2024-01-22 |  | Workshop aligned in the week of 25 Jan
| Taxonomy and Metadata Schema Development | Revised taxonomy and metadata schema was submitted on 14 Dec 2023 Meeting held with Eng. Abdulaziz from PHA Scientific Committee, and he suggested some changes related to mapping between the master table and organizations, remove duplicate variables, and add a lookup table in the ER diagram Team is working on the suggested changes and will be submitting the revised taxonomy by 15 January 2024 | Julien and Vaneja | Final sign off by Caroline Tai |  | 2024-01-15 |  | Submitted
| Data security | We received final comments on data security process from Dr. Majed Necessary changes are done and final editorial review is underway, will submit the deliverable by 05 January | Mohamed Elbelasy | Final sign off by Mohamed Elbelasy |  | 2024-01-05 |  | Submitted
| Data Architecture Design and Functional Requirement Development | Revised report submitted on 15 Nov 2023 PHA suggested to include Genomics application to the overall architecture Suggested changes are done and revised report will be submitted post Maciej's approval The details related to Oracle platform is still awaited, and will be incorporated into the report once received from Oracle | Shouvik and team | Final sign off by Maciej |  | 2024-01-12 |  | Joanne is working on including the Genomic details. Committed to submit the document on 16 Jan. Client submission is 17 Jan.
| Technical requirements development | Revised report submitted on 15 Nov 2023 PHA suggested to include Genomics application to the overall architecture Suggested changes are done and revised report will be submitted post Maciej's approval The details related to Oracle platform is still awaited, and will be incorporated into the report once received from Oracle | Shouvik and team | Final sign off by Maciej |  | 2024-01-12 |  | 16 Jan Oracle requested the meeting..
| Software Product Recommendations | Suggested changes are done and revised report will be submitted post Maciej's approval Apart from this, there are 7 RFPs which needs to be submitted which includes: - Unified Health Data Platform RFP - 6 Surveillance RFP One draft sample RFP (Surveillance) was submitted to PHA on 12 Dec 2023 for feedback and it was suggested on 26 Dec 2023 that all RFPs should reviewed by experts. Team will work with SMEs to take feedback and finalise the RFPs. Will submit all the RFP by 31 Jan 2024 | Shouvik and team | Final sign off on software product recommendation report by Maciej Final sign off on RFPs by SME |  | 12-Jan-24 31-Jan-24 |  | Joanne is working on including the Genomic details. Committed to submit the document on 16 Jan. Client submission is 17 Jan.
Phase.4 | Institutional Governance Structure and Policies | Relook based on strategy which will be developed | Pesh & Michelle | Final sign off by Pesh and Dr Michelle |  | 2024-02-19
| Business processes, policies, and procedures | WIP – preparing for IT department | Hemant | Final sign off by Deepak |  | 2024-02-23
| Manpower and job description | Relook based on strategy which will be developed | Hemant | Final sign off by Pesh and Dr Michelle |  | 2024-03-07
| Data Competency Framework | Relook based on strategy which will be developed | Dr Sangam | Final sign off by Pesh and Dr Michelle |  | 2024-03-11

## Revised timelines (hidden)
Phase | Deliverable name | Status | Editing person | 1st review | 2nd review | Final Review | Target Submission Date | Status
Phase.2 | Current status of the Saudi PHA’s and business assessment | Reviewed by Michelle, needs major revisions and editing and QA | Juliet Ellis | Graziella | Pesh |  | Friday 16 February
| Data Architecture and Functional Current State Assessment | Reviewed by Michelle, needs major revisions and editing and QA | Juliet Ellis | Graziella | Pesh |  | Friday 16 February
| Technical & IT Infrastructure assessment | Submitted to PHA on 14 Dec, waiting for PHA approval | Juliet Ellis | Graziella | Pesh |  | Friday 16 February
| Public health data driven organizations benchmarking and best practices | Re-edited by Pesh, comments received from PHA, needs to be re-edited and QA'd | Juliet Ellis | Graziella | Dr Sadaf (Mon 12 Feb) | Pesh | Friday 16 February
Phase.3 |  | Key stakeholder identified and prepared a draft deck for external stakeholder engagement Stakeholder-wise discussion guide is under process Meetings to be scheduled with these key stakeholders | Pesh/Halima/Michelle
| Final PHA Data Strategy and Operating Model Design based on PHA leader's inputs and external stakeholders workshop inputs |  | Pesh/Halima/Michelle
| Performance Metrics, Key Performance Indicators (KPIs) and Maturity model | KPIs will be defined based on finalised strategy | Pesh/Halima/Michelle
| Implementation Roadmap: the primary activities | Synthesised implementation road map will be developed based on finalised strategy | Pesh/Halima/Michelle
| Data Quality and Data Standards | Next workshop on data quality is to be conducted wherein we will have our expert to oversee steps taken by PHA on current data set and suggest in case any changes are required Refine the deliverable based on workshop and submit | Esther Tolani / Dr Sangam | Sonya Patel | Pesh/Andrea |  | 2024-02-28 |  | Workshop aligned in the week of 25 Jan
| Taxonomy and Metadata Schema Development | Revised taxonomy and metadata schema was submitted on 14 Dec 2023 Meeting held with Eng. Abdulaziz from PHA Scientific Committee, and he suggested some changes related to mapping between the master table and organizations, remove duplicate variables, and add a lookup table in the ER diagram Team is working on the suggested changes and will be submitting the revised taxonomy by 15 January 2024 | Julien and Vaneja | Final sign off by Caroline Tai |  |  | 2024-01-15 |  | Submitted
| Data security | We received final comments on data security process from Dr. Majed Necessary changes are done and final editorial review is underway, will submit the deliverable by 05 January | Mohamed Elbelasy | Final sign off by Mohamed Elbelasy |  |  | 2024-01-05 |  | Submitted
| Data Architecture Design and Functional Requirement Development | Revised report submitted on 15 Nov 2023 PHA suggested to include Genomics application to the overall architecture Suggested changes are done and revised report will be submitted post Maciej's approval The details related to Oracle platform is still awaited, and will be incorporated into the report once received from Oracle | Shouvik and team | Final sign off by Maciej |  |  | 2024-02-16 |  | Joanne is working on including the Genomic details. Committed to submit the document on 16 Jan. Client submission is 17 Jan.
| Technical requirements development | Revised report submitted on 15 Nov 2023 PHA suggested to include Genomics application to the overall architecture Suggested changes are done and revised report will be submitted post Maciej's approval The details related to Oracle platform is still awaited, and will be incorporated into the report once received from Oracle | Shouvik and team | Final sign off by Maciej |  |  | 2024-02-16 |  | 16 Jan Oracle requested the meeting..
| Software Product Recommendations | Suggested changes are done and revised report will be submitted post Maciej's approval | Shouvik and team | Final sign off on software product recommendation report by Maciej Final sign off on RFPs by SME |  |  | 2024-02-16 |  | Joanne is working on including the Genomic details. Committed to submit the document on 16 Jan. Client submission is 17 Jan.
| Surveillance Platforms | Apart from this, there are 7 RFPs which needs to be submitted which includes: - Unified Health Data Platform RFP - 6 Surveillance RFP One draft sample RFP (Surveillance) was submitted to PHA on 12 Dec 2023 for feedback and it was suggested on 26 Dec 2023 that all RFPs should reviewed by experts. | Michelle? |  |  |  | 2024-03-07
Phase.4 | Institutional Governance Structure and Policies | Relook based on strategy which will be developed | Graziella |  |  |  | 2024-02-28
| Business processes, policies, and procedures | WIP – preparing for IT department | Hemant/Graziella |  |  |  | 2024-02-28
| Manpower and job description | Relook based on strategy which will be developed | Dr Sangam |  |  |  | 2024-03-14
| Data Competency Framework | Relook based on strategy which will be developed | Dr Sangam |  |  |  | 2024-03-11

## Deliverable Tracker_v0.1
Deliverable submitted AND signed off by PHA
Deliverable still being delivered
Deliverable not delivered
Phase | Deliverable name | Status updates 25/06/2025 | Editing person | 1st review | 2nd review | Final sign-off | Submission Date | Status
Phase 2
Phase 2 | Current status of the Saudi PHA’s and business assessment | Juliet has finished re-editing. PD to conduct final review and then ready to submit this weekend | Juliet Ellis | Graziella | Pesh | Deepak | 2024-02-17 | 3
| Data Architecture and Functional Current State Assessment | Juliet has re-edited/Pesh has also re-edited. Juliet for final format check | Juliet Ellis | Pesh | Pesh | Deepak | 2024-02-17 | 3
| Technical & IT Infrastructure assessment | Pesh has reviewed. No signature page required. | Juliet Ellis | Graziella | Pesh | Deepak | 2024-02-17 | 3
| Public health data driven organizations benchmarking and best practices | Sent to Sadaf for final review Thursday 22 Feb, with 1 day turnaround. Received feedback on Sunday 25 Feb. Will submit final version on Monday 26 Feb | Juliet Ellis | Sadaf | Juliet | Deepak | 2024-02-26 | 3
Phase 3
Phase 3 | Final PHA Data Strategy based on PHA leader's inputs and external stakeholders workshop inputs | PHA want a final designed document that can be published on the website. Next steps is to agree a design format that they are happy with. | Pesh/Halima | Michelle | Halima | Pesh |  | 1900-01-01
| Performance Metrics, Key Performance Indicators (KPIs) and Maturity model | PHA want a final designed document that can be published on the website. Next steps is to agree a design format that they are happy with. | Pesh/Halima/Michelle | Michelle | Halima | Pesh |  | 1900-01-01
| Implementation Roadmap: the primary activities | PHA have comments - will share comments by the end of this week | Juliet Ellis /Dr Sangam | Michelle | Halima | Pesh |  | 1900-01-01
| Data Quality and Data Standards | Pesh to share updated Quality Report this week. To schedule a meeting with IQVIA Quality Report team and PHA review team to align on expectations and agree next steps. | Esther Tolani / Dr Sangam | kendall supporting Esther | Pesh | Andreas |  | 1900-01-01
| Taxonomy and Metadata Schema Development | Pesh to let Ola and team know of timelines for finalising the data dictionary as per the email yesterday. | Julien and Vanaja | Final sign off by Caroline Tai |  |  |  | 1900-01-01
| Data security | Final Report submitted 05/01/2024 - PHA signed off | Mohamed Elbelasy | Final sign off by Mohamed Elbelasy |  |  | 2024-03-11 | 1900-01-02
| Data Architecture Design and Functional Requirement Development | Final report submitted 17/02/2024 - PHA signed-off | Shouvik and team |  |  | Maciej | 2024-02-17 | 1900-01-02
| Technical requirements development | Final report submitted 17/02/2024 - PHA signed-off | Shouvik and team |  |  | Maciej | 2024-02-17 | 1900-01-02
| Software Product Recommendations | Final report submitted 17/02/2024 - PHA signed-off - Oracle and Cloudera vendor responses included as Annexes - It was agreed that budget figures will go into a resource (includinging financial) requirements document. | Shouvik and team |  |  | Maciej | 2024-02-17 | 1900-01-02
| Surveillance Platforms | Apart from this, there are 7 RFPs which needs to be submitted which includes: - Unified Health Data Platform RFP - 6 Surveillance RFP One draft sample RFP (Surveillance) was submitted to PHA on 12 Dec 2023 for feedback and it was suggested on 26 Dec 2023 that all RFPs should reviewed by experts. - Dr Khalid's recommendation is to focus on the technical requirements and not the legal or other components of an RFP. As Procurement department of PHA will cover those elements. - Meeting with Suliman and Simon 07/03/24 - What is required is a framework, rather than a just RFPs, we will also need to spill out a step by step implementation plan. | Michelle | External advisor review | Michelle | Pesh | 2024-03-21 | 1900-01-01
Phase 4
Phase.4 | Institutional Governance Structure and Data Management Office (DMO) | completed - PHA signed-off | Graziella | Juliet | Dania | Pesh | 2024-03-08 | 3
| Business processes, policies, and procedures | completed - PHA signed-off | Dania | Graziella | Juliet | Pesh | 2024-03-08 | 3
| Manpower and job description | completed - PHA signed-off | Dr Sangam | Graziella |  | Pesh | 2024-03-14 | 3
| Data Competency Framework | completed - PHA signed-off | Dr Sangam | Graziella |  | Pesh | 2024-03-14 | 3
| Recommendations for development data competency and training for business and data stakeholders | completed - PHA signed-off | Helen Brown - IKT company |  |  |  | 2024-04-30 | 3
Additional work to be completed
| Proof of Concept | Underway - PHA to share data with IQVIA as next step | [5 empty] | 2
| Outstanding training ( 4 sessions) | Underway - ITK to deliver 3 sessions, Dr JF to deliver 1 | [5 empty] | 2
| RFP for Surveillance Platform (Disease and Risk) | IQVIA to develop an RFP for a surveillance platform - use work already undertaken by Dr Sangam and Dr Simon | [5 empty] | 2